# NIL Youth Sports Platform — Execution Plan (v2)

Document version: 2.0 — supersedes v1 build order Date: 2026-09-30 Authority: see §0.2 Companion: SPEC_AMENDMENTS.md (the patch list that makes the source spec set consistent with this plan) Predecessor analysis: SPINOFF_MVP_ANALYSIS.md (findings F1–F12 referenced throughout)

## 0. How to Use This Plan

### 0.1 Scope

| Dimension | Value |
| --- | --- |
| MVP boundary | Stages 0–9 (Implementation Phases 1–3), delivered API-first |
| Stage 10 | Post-MVP (Phase 4) — outline only, no estimates |
| Build order | Hybrid: extract API + schema (S1–S3), build and validate a vertical slice (S4–S5), then complete web extraction (S6) and feature breadth (S7–S9) |
| Relationship to source platform | Pattern replication — the spinoff reuses the source architecture, including the FlexibleApiSingleton hierarchy |
| Estimate | 39.5–73 engineer-weeks, likely ~56 (§6) |

### 0.2 Authority & supersession

| Document | Status after this plan |
| --- | --- |
| PROJECT_SEQUENCE.md | Superseded as build order. Retained as historical record and as the stage→source traceability map (§9) |
| IMPLEMENTATION_PLAN.md | Superseded as task backlog. Its skill index (§0.1) and Definition of Done (§0) are retained and incorporated into §2.4 and §7 |
| TECHNICAL_SPEC.md | Remains authoritative for architecture, DDL, capability design, and the §12 gap analysis — as amended by SPEC_AMENDMENTS.md |
| MIGRATION_DESIGN.md | Remains authoritative for the extraction inventory (KEEP/DROP lists, file counts) — as amended |
| FRONTEND_SPEC.md | Remains authoritative for UI surfaces, components, and navigation — as amended |
| SPINOFF_MVP_ANALYSIS.md | Findings register. Every finding F1–F12 is closed by a task or a gate in this plan (§8) |

Conflict rule. If any document contradicts this plan, this plan wins. If this plan is silent, SPEC_AMENDMENTS.md is authoritative over the original spec text. If both are silent, the source platform's actual behavior wins over all documents (per finding F1 — this rule exists because the spec set asserted a mechanism that does not exist).

### 0.3 Work units

| Unit | Definition |
| --- | --- |
| ew | engineer-week = 1 person × 5 focused days, inclusive of design, implementation, review, and the task's acceptance gate |
| Task | Smallest unit that can be independently verified. Has an ID, dependencies, deliverable, acceptance, effort, and confidence |
| Stage | A group of tasks with a single entry gate and exit gate |
| Gate | A hard stop. Cannot be passed on "mostly working." Requires the named evidence artifact |

### 0.4 Confidence ratings

| Rating | Meaning | Planning use |
| --- | --- | --- |
| High | Comparable work has been done in this codebase; scope is enumerable | Use the estimate |
| Medium | Scope is enumerable but execution has unknowns | Use the estimate, add 20% buffer |
| Low | Scope depends on coupling that has not been measured | Do not commit. Measure first (spike, S0.1) or re-baseline after S5 |

Low-confidence stages in this plan: S2, S3, S6, S9. Together they are ~44 ew of the ~56 ew midpoint. That is the honest shape of the risk.

## 1. Decisions Ledger

Every decision below has a recommended default. The plan is executable immediately by accepting defaults; each may be overridden before its "Decide by" stage. Decisions marked [SIGN-OFF] require a human (legal, finance, or product owner) — they are not the implementer's to make.

| ID | Decision | Recommended default | Rationale | Blocks | Decide by | Owner |
| --- | --- | --- | --- | --- | --- | --- |
| D1 | Is RLS the Phase-2 isolation guarantee or Phase-4 hardening? | Phase-4 hardening. Phase-2 enforcement = explicit WHERE tenant_id + a repository-level tenant guard (S4.1) | The source platform has no RLS (F1). Promising it in Phase 2 means promising a control that does not exist. The tenant guard gives equivalent bug-catch power at a fraction of the cost | S2, S4 | S0 | Eng lead |
| D2 | Athlete-tenants: widen tenants or side table? What tier do they carry? | Add tenant_type + a nil_tenant_profile side table. Seed a platform_default tier row; force directory_visible = false for tenant_type='athlete' | tenants is commerce-shaped (Stripe slots, SKU quotas, GBP tokens). Athletes must not inherit those columns or public directory eligibility (F2) | S2 | S0 | Eng lead |
| D3 | Which base-singleton chain is canonical? Are V2/Stable deleted? | UniversalSingleton → EnhancedFlexibleApiSingleton → FlexibleApiSingleton → {Public, Tenant, Customer, Admin, Authenticated} is canonical. Delete FlexibleApiSingletonV2, FlexibleApiSingletonStable, PublicApiSingletonStable | The spec's §13 hierarchy targets this chain. Three coexisting chains is drift, not a feature (F5) | S0 (hygiene), S3, S6 | S0 | Eng lead |
| D4 | Rename orders/order_items/payments, or create nil_deals/nil_deal_milestones/nil_payments fresh? | Create fresh, delete commerce models, reuse the services | On a fresh DB the rename buys nothing and drags Stripe/refund/tax/shipment entanglement along (F7) | S2, S3 | S0 | Eng lead |
| D5 | Can an athlete-tenant appear in tenant-directory / discovery / storefront-discovery surfaces? | No — ever. Explicit exclusion rule + directory_visible = false default + a regression test | directory_visible defaults true; athlete-tenants would otherwise be publicly discoverable (F2, F9) | S2, S4 | S0 | Eng lead + product |
| D6 | Are nil_guardian / nil_fan_network capability-gated or platform-default? | Platform-default, not tier-gated (per §12.9). Remove them from the capability registry and delete the corresponding hooks from FRONTEND_SPEC.md §13a.11 | §7 and §12.9 contradict each other; §12.9 is the correct policy (never paywall the trust/safety and engagement layer) (F6d) | S9 | S4 | Product owner [SIGN-OFF] |
| D7 | How does right-to-erasure coexist with an append-only audit trail? | Audit rows carry pseudonymous references only — never PII. Erasure rewrites the reference, not the log | Both requirements are legally load-bearing and the spec never reconciles them. Resolving it at schema time is cheap; later it is a migration (F9) | S2 | S0 | Eng lead + legal [SIGN-OFF] |
| D8 | Test strategy: harness, CI gates, jsdom-or-not for web? | vitest everywhere. CI gates: typecheck, raw-fetch, UUID/Date.now() id, PII-under-/api/public/*. Web = server-render assertions only for now (matches existing AGENTS.md constraint) | "Release-blocking P0 tests" must not be built after the features they guard (F10) | S0, S4 | S0 | Eng lead |
| D9 | Fee parameters: platform %, guardian split, non-profit slice, payer-keyed tier matrix | Defer. Model is already settled (§12.10 — deal = purchase, transaction fee). These are parameters | Confirmed non-blocking: parameter tuning, not architecture. Must be closed before S9 finance work, not before S1 | S9 only | S8 | Finance [SIGN-OFF] |
| D10 | Legal sign-off on COPPA / FERPA / state-NIL / erasure design | Start immediately. External dependency, longest lead time | Hard-gates the schema freeze (S2). Slipping this slips everything | S2 | S0 (start) | Legal [SIGN-OFF] |
| D11 | Is a pilot dataset to be carried over? | Assume no — new Supabase project is empty | The whole plan assumes no data migration. If this is wrong, every estimate is void | S2 | S0 | Product owner |

Rule: a stage does not begin while a decision it depends on is open. If a decision is not made by its "Decide by" stage, the recommended default is adopted in writing and the plan proceeds — no stage blocks on silence.

## 2. Delivery Model

### 2.1 Stage flow

S0 Baseline ──► S1 Infra ──► S2 Schema ──► S3 API Extraction ──┬──► S4 Safety Substrate
                                                                │            │
                                                                │            ▼
                                                                │    S5 ★ VERTICAL SLICE ★   (G5 — architecture validated)
                                                                │            │
                                                                │            ▼  (re-baseline S6–S9 from measured velocity)
                                                                │    S6 Web Extraction ──► S8 Native Pipeline ──► S9 Unified Service
                                                                │                                                       │
                                                                │                                                       ▼
                                                                │                                              S10 Post-MVP (outline)
                                                                │
                                                                └──► S7 Credibility Shell   ◄── RECOMMENDED: pull forward,
                                                                     (parallel with S4–S5)      investor demo at ~3 months

Why this order (the hybrid choice). Worth being precise about the gain rather than overselling it.

- Architectural feedback arrives at a similar time. G5 lands at ~25 ew cumulative (S0–S5 mid). Under the spec's order, the equivalent validation lands at ~28 ew (A–D plus E, before Phase 2 begins). The feedback is not dramatically earlier — anyone claiming a large timing win is misreading the plan.

- What genuinely improves is what you are holding when the feedback arrives. This plan validates before the low-confidence destructive web strip (S6, ~9 ew) and never breaks the web app — it stays demoable from S1 onward. The spec's order strips the web app to zero before anything has been proven. If the architecture is wrong here, you correct a working app and a rebuilt API; under the spec's order you correct a half-destroyed one.

- A third benefit, easily missed: the API is built once, against a design that has been validated, rather than speculatively and then reworked.

Sequencing option — pull the Credibility Shell forward (recommended). S7 (landing + lead capture + nil_landing) has no dependency on the slice. It needs only S1 (infra), S2 (the nil_leads_list table), and S3.5/S3.7 (resolver plumbing + the lead service). Because Implementation Phase 1 is explicitly investor-facing, S7 should be executed immediately after S3, in parallel with S4–S5.

- Effect: an investor-ready public shell at ~21 ew cumulative instead of ~36.5 ew — roughly 3 months instead of 8.

- Trade-off: nil_landing (tier-only, no merchant prefs) becomes the template-setting capability rather than nil_roster. A simpler reference is acceptable, and arguably preferable as a first pass.

- It does not disturb the G5 gate, the P0 suite, or the post-G5 re-baseline rule.

Serialization reality. S2 → S3 → S4 → S5 is a hard chain and cannot be widened. S7 can move (above). S6 and S9 parallelize well. Plan staffing around the chain, not around the total.

### 2.2 Additive-then-subtractive rule (optimization O4)

Never delete a Prisma model before the code that references it is gone. The spec's M1/M2 split deletes models and code in the same pass, which means every deletion batch produces a cascade of type errors from both directions at once.

Mandated order:

- Add all NIL models (additive — breaks nothing). prisma validate green.

- Delete commerce code in vertical batches, checkapi green after each batch.

- Then drop commerce models, grep proving zero references remain.

This converts one large entangled repair into two ordered, independently-verifiable repairs.

### 2.3 Definition of Done

Per task (inherited from IMPLEMENTATION_PLAN.md §0, retained):

- pnpm checkapi and pnpm checkweb pass with zero TS errors (verified baseline — both green today)

- The task's named acceptance check passes

- No raw fetch introduced (web → makeDefaultRequest; API → UniversalSingleton helpers)

- No randomUUID() / Date.now() IDs — all IDs from id-generator.ts

- Exception (documented): bot_* tables retain @db.Uuid + gen_random_uuid() per TECHNICAL_SPEC.md §14.12. The grep gate must whitelist apps/api/src/services/bot/ and the bot route directory, or the gate fails on compliant code (F6c)

Per stage: the exit gate's evidence artifact exists and is attached to the stage PR.

Per capability (the 8-phase pipeline, from TECHNICAL_SPEC.md §7 — corrected paths per F4):

- Define feature keys + tier assignment in the seed scripts (apps/api/prisma/seed-*-capabilities.ts, seed-tiers.ts) — not canonical-features.ts / tier-hierarchies.ts, which do not exist

- Seed features_list → capability_features_list → tier_features_list

- Store prefs tenant_nil_*_options_settings model + table

- Resolve resolveNilXxx() + wire EffectiveCapabilityResolver.ts + add the disabled entry to buildExpiredCapabilitiesResponse

- Route nil-xxx-options-settings.ts (GET { success, settings, tierState }; PUT tier-validates + invalidateEffectiveCapabilities)

- Map UnifiedCapabilityService.mapNilXxx() + state interface + useNilXxxCapability hook

- Display PlanSummaryPanel + CapabilityShowcase (correct group-level merchantGated counting)

- Verify checkapi + checkweb + verify-capability-deployment checklist

### 2.4 Standing engineering rules

| Rule | Enforcement |
| --- | --- |
| No raw fetch in NIL code paths | CI grep gate |
| No randomUUID/Date.now() IDs (bot exception above) | CI grep gate |
| No PII fields on /api/public/* | CI grep gate + S4.6 enumeration script |
| Concrete NIL services extend a NIL base, never UniversalSingleton directly | CI check (F5 — prose rules demonstrably did not hold in the source repo) |
| Every minor-data mutation enumerates all cache namespaces | cross-context-cache-invalidation.md + S4.4 contract + test |
| Every status/consent/deal/payout transition emits an X-Audit-ID | structured-logging.md + S4.8 |
| Before building any nil_* capability, open its commerce analog and copy the structure | Task-level checklist item (the spec's own §7.1 rule, made explicit) |

## 3. Gates

Each gate has an evidence artifact — a file, test run, or report attached to the stage. "Passed" without the artifact is not passed.

| Gate | After | Exit criteria | Evidence artifact |
| --- | --- | --- | --- |
| G0 | S0 | Spike report with measured repair ratio; green baseline captured; CI gates running; D1–D5, D7, D8, D11 closed; D10 legal review formally started; live-DB object inventory complete | spike-report.md, baseline-typecheck.txt, CI config committed, db-object-inventory.md |
| G1 | S1 | Unmodified fork deploys to Railway + Vercel; Auth0 login→dashboard→logout round-trips for all 8 roles; doppler secrets lists every required key in all 3 configs; zero old-brand strings | deploy logs, Auth0 role screenshot set, grep output |
| G2 | S2 | prisma validate green; NIL wave-1 tables created on the new DB; seeds run idempotently; API still compiles (additive only — no deletions yet); tenant_type + nil_tenant_profile + platform_default tier present; directory_visible=false for athlete type | prisma validate output, seed logs, checkapi output |
| G3 | S3 | checkapi green; zero commerce route/service references; commerce Prisma models dropped with grep proof of no references; 19 ID generators with tests; resolver registry dispatches; 8 NIL roles validate | checkapi output, grep proofs, generator test run |
| G4 | S4 | Tenant guard rejects a query against an athlete-owned table with no tenant predicate (proven by test); consent engine handles grant/revoke/most-restrictive-wins; visibility state machine enforces all transition guards; cache contract enumerated; PII enumeration script runs in CI; negative-path harness executes | test run, CI log, pii-surface-report.md |
| G5 ★ | S5 | Architecture validated. Slice demo: guardian provisions athlete-tenant → grants scoped consent → passes moderation + compliance → profile appears on public roster → revoke removes it within one request. All P0 negative tests green. PII gate green | demo recording, P0 test run, PII report |
| G6 | S6 | checkweb green; zero commerce web references; 7 NIL bases + web services in place on the canonical chain; proxy/auth/capability-service/rbac/nav updated; rebrand complete (no VisibleShelf strings) | checkweb output, grep proof, brand audit |
| G7 | S7 | Landing live on the NIL domain over TLS; lead intake writes and is not publicly readable; nil_landing capability resolves + R13 expired-manifest returns 200 disabled | TLS check, lead write test, capability route test |
| G8 | S8 | M2 milestone: media/metrics/achievements live; institution roster management; manual compliance verdict workflow; every P0 negative-path test from §12.12 green | full P0 suite run |
| G9 | S9 | All personas have scoped portals; 5 persona capabilities deployed (8 phases each); CRM + bot live with child-safety guardrails; invitations + onboarding working end-to-end; every adult↔minor interaction guardian-gated | capability checklists ×5, P1 suite run, invitation E2E |

★ G5 is the decision gate. After G5, re-baseline S6–S9 from measured velocity (§6.5). Do not commit to the S6–S9 numbers before then.

## 4. Stages

### Stage 0 — Baseline, Hygiene & Decisions

Entry: none. Exit: G0. Estimate: 1.5–2.5 ew.

| ID | Task | Depends | Deliverable | Acceptance | ew | Conf |
| --- | --- | --- | --- | --- | --- | --- |
| 0.1 | Extraction spike (de-risking): on a throwaway branch, delete one complete commerce vertical (inventory/ recommended), repair until checkapi and checkweb are green. Record files deleted, files edited, errors surfaced, wall-clock | — | spike-report.md with measured repair ratio per vertical | Ratio extrapolates to the full DROP list; two lowest-confidence stage estimates replaced with measured numbers | 0.6–1.0 | High |
| 0.2 | Capture green baseline: checkapi + checkweb outputs; record file/LOC/model counts | — | baseline-typecheck.txt, baseline-metrics.txt | Artifacts committed; baseline reproducible | 0.1 | High |
| 0.3 | Install CI gates: typecheck, raw-fetch, UUID/Date.now() id, PII-under-/api/public/*, prisma validate, "NIL service must extend a NIL base" | 0.2 | CI config committed | Each gate fails on a deliberately-introduced violation (gate-testing the gate) | 0.3–0.5 | High |
| 0.4 | Hygiene purge: 509 .bak/.backup files, 3 backup Prisma models (subscription_tiers_list_v1_backup, tier_features_list_v1_backup, tenants_metadata_backup_gbp), abandoned singleton variants per D3, stray baseline dumps | D3 | Clean tree | grep -cE "\.(bak\¦backup)$" → 0; prisma validate green; checkapi/checkweb still green | 0.5–1.0 | High |
| 0.5 | Live-DB object inventory: enumerate triggers, policies, views, materialized views, extensions from the live Supabase DB — not from schema.prisma | — | db-object-inventory.md | Inventory reconciles against schema.prisma; every out-of-band object listed with a keep/drop decision | 0.2–0.4 | High |
| 0.6 | Close the decisions ledger (D1–D5, D7, D8, D11) or adopt defaults in writing | — | Signed-off ledger | Every blocking decision has a written answer or an adopted default | 0.1 | High |
| 0.7 | Start legal review (D10) — external, longest lead time | — | Legal engagement confirmed + target date | Review formally opened and tracked as an S2 dependency | — | — |

Why 0.1 before everything. The estimate's uncertainty is concentrated in the deletion-and-repair tax. A 3–5 day measurement replaces the two lowest-confidence rows with measured numbers and typically halves the total range. It also produces the coupling map (which retained subsystems touch dropped models) that S2 needs anyway.

Why 0.4 is not optional. 509 backup files and three backup Prisma models make every downstream grep gate noisy, and leave duplicate-looking models a junior agent can mistake for the real one. It is 0.5–1.0 ew that improves every subsequent verification step.

### Stage 1 — Infrastructure

Entry: G0. Exit: G1. Estimate: 1–2 ew. (= spec Stage A)

| ID | Task | Deliverable | Acceptance | ew | Conf |
| --- | --- | --- | --- | --- | --- |
| 1.1 | New git repo; clone source files without .git history | Clean repo, single initial commit | git log shows one commit | 0.1 | High |
| 1.2 | New Supabase project; CREATE EXTENSION vector | Provisioned project | Dashboard accessible; extension present | 0.2 | High |
| 1.3 | New Auth0 tenant + 8 roles (athlete, guardian, institution_admin, coach, sponsor, fan, platform_admin, compliance_auditor); callback + logout URLs | Configured tenant | All 8 roles visible; login round-trips locally | 0.3–0.5 | Medium |
| 1.4 | New Vercel project (web) | Linked project | Preview deploy succeeds | 0.1 | High |
| 1.5 | New Railway service (api) | Linked service | Service deploys | 0.1 | High |
| 1.6 | Doppler: local, dev, prd configs with all secrets | Three configs | doppler secrets lists every required key in each | 0.2–0.4 | Medium |
| 1.7 | Package rename (@rvp/* → @nil/*); brand strings; PLATFORM_DOMAINS; API_BASE_URL defaults | Renamed packages | pnpm install succeeds; zero old-brand references | 0.2–0.4 | High |
| 1.8 | Prove the unmodified fork deploys to both targets | Deploy logs | Both targets serve; API health check passes | 0.1–0.2 | High |

Task 1.8 is the real point of this stage. Deploying before any deletion separates "the fork is broken" from "our extraction broke it." Without it, the first deploy failure in S3 is ambiguous.

### Stage 2 — Schema Foundation

Entry: G1. Exit: G2. Estimate: 4–8 ew. (= spec Stage B, re-scoped: additive only)

This stage adds. It does not delete. Per §2.2, commerce model removal happens in S3.6, after the code that references those models is gone.

| ID | Task | Depends | Deliverable | Acceptance | ew | Conf |
| --- | --- | --- | --- | --- | --- | --- |
| 2.1 | Wave-1 schema (slice-critical): enums; tenants.tenant_type; nil_tenant_profile; athlete_profiles_list; guardians_list; guardian_athlete_links_list; consent_records_list; highlight_media_list; nil_leads_list; the *_options_settings base | D2 | Migration nil_wave1 | prisma validate green; tables created; athlete provisions as a tenant | 1.0–2.0 | Low |
| 2.2 | Wave-2 schema (breadth): athlete_metrics_list, athlete_achievements_list, athlete_tenant_memberships_list, recruiting_boards_list, scout_ratings_list, sponsorship_deals_list, escrow_milestones_list, nonprofit_allocation_pools_list, nil_eligibility_rules_list, moderation_cases_list, message_threads_list, fan_badges_list, data_erasure_requests_list, payout_schedules_list, sponsor_spend_limits_list, nil_offers_list, nil_events_list, nil_invitations_list, nil_onboarding_sessions_list, 7 × tenant_nil_*_options_settings | 2.1, D4 | Migration nil_wave2 | prisma validate green; table count reconciles against TECHNICAL_SPEC.md §14 counted directly (the plan's list undercounts — F12) | 1.5–3.0 | Low |
| 2.3 | platform_default tier + NIL feature/capability/tier seed scripts | D2, D6 | Seed scripts | Athlete/guardian/fan features resolve from platform default, never tier_features_list | 0.5–1.0 | Medium |
| 2.4 | Seed base data: NIL eligibility rules, navigation links, bot guardrails (child-safety) | 2.2 | Seed scripts | All base data present; seeds idempotent | 0.5–1.0 | Medium |
| 2.5 | mv_athlete_discovery materialized view + its scoping review | 2.2, D5 | View + refresh function + scoping note | View queryable; proven to exclude unapproved and directory_visible=false rows (F9) | 0.3–0.6 | Medium |
| 2.6 | Guardian-required trigger (nil_require_guardian_for_minor) on CRM tables | 2.2 | Trigger | Minor-subject CRM record without guardian → DB error | 0.2–0.4 | High |
| 2.7 | Audit-trail schema per D7 (pseudonymous references; erasure reconciliation) | D7 | Schema + design note | Erasure can rewrite references without falsifying the log | 0.2–0.4 | Medium |
| 2.8 | RLS decision applied (D1): if Phase-4 hardening, write the deferral record; if Phase-2, build the policies and the transaction-mode GUC workaround | D1 | rls-decision.md (+ policies if option 2) | Decision recorded with rationale; if built, isolation test passes non-vacuously (proves rows are visible with the right tenant set) | 0.2–0.4 / +3–6 | Medium |

F1 closure note. MIGRATION_DESIGN.md §3.4 currently states RLS "carries over unchanged." It does not exist. If you take the default (D1 = Phase-4 hardening), 2.8 is a short design record and the Phase-2 guarantee is the S4.1 tenant guard. If you take option 2, budget it here honestly — ~24 tables × (policy + GUC plumbing + Supabase transaction-mode workaround + non-vacuous isolation tests) is its own workstream.

F12 closure note. Count the tables from TECHNICAL_SPEC.md §14 directly. The plan lists 22; the migration design lists 25; the spec contains 23 CREATE TABLE statements plus the options tables. Reconcile before writing the migration.

### Stage 3 — API Extraction & Core

Entry: G2. Exit: G3. Estimate: 6–12 ew. (= spec Stage C)

| ID | Task | Depends | Deliverable | Acceptance | ew | Conf |
| --- | --- | --- | --- | --- | --- | --- |
| 3.1 | Delete commerce routes in vertical batches (products, inventory, storefronts, shops, directory, GBP, GMC, barcode, cart, shipments, business hours, feed, store reviews, featured, social commerce, recommendations, image enrichment, clone, quick-start, publishing, digital downloads, catalog adoption, cross-tenant products, location availability, deposit forfeiture, smart-sale tagging, slug gen, override analytics) | 0.1 (spike ratio), 0.3 | Deleted routes | checkapi green after each batch; no broken mounts in index.ts | 2.0–4.0 | Low |
| 3.2 | Delete commerce services + middleware (image-search-limits.ts, sku-limits.ts) + commerce-specific test/doc files | 3.1 | Deleted services | checkapi green | 1.5–3.0 | Low |
| 3.3 | 19 NIL ID generators + table-driven tests | 3.2 | id-generator.ts entries + tests | All formats match §6; collision check done; test covers every generator | 0.3–0.6 | High |
| 3.4 | NIL resolver registry: NilLandingResolver, NilRosterResolver, NilGuardianResolver, NilRecruitingResolver, NilSponsorshipResolver, NilAchievementsResolver, NilFanNetworkResolver, NilComplianceResolver, NilFinanceResolver, NilCrmOptionsResolver, NilBotOptionsResolver | 3.3 | Resolver files | Each returns the correct capability shape. Build the first one by copying its commerce analog, then template the rest (O2) | 1.0–2.0 | Medium |
| 3.5 | Rewire EffectiveCapabilityResolver.ts: NIL imports, MerchantSettingsBundle type, dispatch, buildExpiredCapabilitiesResponse disabled entries | 3.4 | Updated orchestrator | resolveEffectiveCapabilities() dispatches to NIL resolvers; R13 expired manifest returns 200 disabled | 0.3–0.6 | Medium |
| 3.6 | Drop commerce Prisma models (second wave, per §2.2) — only after grep proves zero references | 3.1, 3.2 | Reduced schema.prisma | grep proof of zero references; prisma validate green; checkapi green | 0.5–1.0 | Medium |
| 3.7 | Phase-1/2 NIL backend services: NilLeadService, AthleteProfileService, GuardianConsentService, MediaModerationService, NilRosterService, ComplianceVettingService (manual verdict) | 3.5 | Services | Non-consent_authority write → 403; non-allowlisted host rejected | 1.5–3.0 | Medium |
| 3.8 | Auth middleware + 8 NIL roles (auth.ts, role-validation.ts, permissions.ts) | 1.3 | Updated middleware | All 8 roles validate correctly | 0.3–0.6 | Medium |
| 3.9 | Route mounting in index.ts: remove commerce mounts, add NIL mounts | 3.1, 3.7 | Updated entry | Server starts without errors | 0.2–0.4 | High |

O2 — template-first capability (the single largest effort saver). Task 3.4 builds eleven resolvers. Do not design them independently. Build NilRosterResolver by copying its commerce analog end to end, get it through the 8-phase pipeline (S5.5), then produce the remaining ten by analogy against that reference. Eleven independent designs is the failure mode; one reference plus ten analogies is roughly half the cost.

### Stage 4 — Safety Substrate

Entry: G3. Exit: G4. Estimate: 2–4 ew. (new stage — F1, F9, F10)

This stage exists because the spec treats its safety controls as features of Phase 2 rather than as an enforcement layer that Phase 2 features are built on. Building the layer first means every subsequent feature inherits it, instead of each feature re-implementing (and subtly mis-implementing) tenant scoping, consent checks, and cache eviction.

| ID | Task | Depends | Deliverable | Acceptance | ew | Conf |
| --- | --- | --- | --- | --- | --- | --- |
| 4.1 | Repository-level tenant guard (D1): a Prisma middleware/wrapper that rejects any query against an athlete-owned table without a tenant predicate | D1 | Guard module | Test: a query against athlete_profiles_list with no tenant_id is rejected at runtime. This is the Phase-2 substitute for RLS (F1) | 0.5–1.0 | Medium |
| 4.2 | Consent engine: versioned scoped consent; consent_authority checks; most-restrictive-wins across multiple guardians; revocation cascade contract | 2.1 | GuardianConsentService core + tests | Grant/revoke/veto all tested; any owning guardian can veto; cascade contract enumerated | 0.5–1.0 | Medium |
| 4.3 | Visibility firewall state machine + transition guards (draft→pending→approved→archived, pending→rejected) | 2.1 | State machine module | Transition to approved requires all three gates true; illegal transitions rejected | 0.3–0.6 | Medium |
| 4.4 | Cache-invalidation contract: namespace enumeration + getServiceCachePatterns / invalidateServiceCaches + eviction test | 4.2, 4.3 | Contract + test | Approve → roster reflects within one request; revoke evicts every namespace (partial eviction = safety incident) | 0.3–0.6 | Medium |
| 4.5 | Media moderation core + host allowlist (parseVideoUrl pattern) | 2.1 | Service + allowlist | Non-allowlisted host rejected; media cannot publish unmoderated | 0.2–0.4 | High |
| 4.6 | PII / public-surface enumeration script (optimization — automated, not a manual audit): walks all retained read paths (routes, materialized views, nav data, email templates, Sentry config, analytics, sitemap/preview) and reports any athlete/guardian field reachable | 2.5 | pii-surface-report.md + CI gate | Script runs in CI; report enumerates every surface; no unclassified surface remains (F9) | 0.4–0.8 | Medium |
| 4.7 | Negative-path test harness (DB-level + API-level) for the P0 suite | D8 | Harness | The five P0 tests from §12.12 can be written and executed against it (F10) | 0.3–0.6 | Medium |
| 4.8 | Audit trail implementation per D7: X-Audit-ID emission on every status/consent/deal/payout transition | D7, 2.7 | Logging integration | Every transition emits an audit id; audit rows contain no PII | 0.2–0.4 | Medium |

F9 closure. The spec's PII strategy covers DTO projections. Task 4.6 covers the paths a DTO test cannot reach: the materialized view, the directory default, DB-driven nav, email templates, error reporting, analytics, and sitemap/preview surfaces.

F10 closure. Task 4.7 is scheduled before the features it guards, not after.

### Stage 5 — Vertical Slice Validation ★

Entry: G4. Exit: G5 (the decision gate). Estimate: 2.5–4.5 ew. (= the spec's "First Executable Slice," expanded to include its web consumer)

| ID | Task | Depends | Deliverable | Acceptance | ew | Conf |
| --- | --- | --- | --- | --- | --- | --- |
| 5.1 | Athlete-tenant provisioning (guardian-initiated) + COPPA age-band gate | 4.1, 4.3 | Provisioning path | Athlete-initiated under-13 intake → 403 | 0.4–0.7 | Medium |
| 5.2 | Guardian link + scoped consent grant/revoke through the private 0-TTL path | 4.2 | Consent flow | Non-consent_authority write → 403; scoped grants enforced | 0.3–0.5 | Medium |
| 5.3 | Visibility state machine end-to-end on a real profile | 4.3, 5.1, 5.2 | Working transitions | Only all-three-gates-true reaches approved | 0.3–0.5 | Medium |
| 5.4 | Public roster route: approved-only, consent-filtered, PII-stripped | 5.3 | NilRosterService + route | Zero records when no row is approved; GPA visible only with gpa_display consent | 0.4–0.7 | Medium |
| 5.5 | nil_roster + nil_compliance capabilities, full 8 phases — the reference implementation (O2) | 3.4, 3.5, 5.4 | Capability end-to-end | verify-capability-deployment checklist passes; R13 expired manifest works | 0.6–1.0 | Medium |
| 5.6 | Per-athlete cache eviction on status/consent change | 4.4 | Eviction wiring | Approve → roster reflects within one request; revoke → gone within one request | 0.2–0.4 | Medium |
| 5.7 | P0 gates: under-13 self-register 403; consent revocation cascade; media moderation gate | 4.5, 4.7 | P0 tests green | All three negative paths pass | 0.3–0.6 | Medium |
| 5.8 | Web slice (additive only): NilPublicApiSingleton, AthleteApiSingleton, GuardianApiSingleton, NilPublicRosterService, AthleteService, GuardianService + a minimal public roster page | D3, 5.4 | Web slice | Slice renders against the live API; no commerce code deleted yet (hybrid property) | 0.7–1.2 | Medium |

★ G5 is where the architecture gets validated. If athlete-as-tenant, the tenant guard, scoped consent, the firewall, capability gating, and the P0 gates all hold on this thin path, the remaining ~40 ew is execution rather than discovery. If any of them does not hold, you have spent ~10 ew instead of ~26 to find out.

Task 5.8 keeps the hybrid property. The web app is additive here — the slice's consumers are new files. Commerce web code is still present and still compiling. Destructive web extraction is S6.

### Stage 6 — Web Extraction & Core

Entry: G5 + re-baseline (§6.5). Exit: G6. Estimate: 6–12 ew. (= spec Stage D)

| ID | Task | Depends | Deliverable | Acceptance | ew | Conf |
| --- | --- | --- | --- | --- | --- | --- |
| 6.1 | Delete commerce web routes in batches (/products/*, /shops/*, /directory/*, /items/*, /cart/*, /carts/*, /checkout/*, /orders/*, /my-orders/*, /downloads/*, /catalog/*, /category-discovery/*, /cross-tenant/*, /test-*, /debug/*, /sentry-example-page/*) | G5, 0.1 ratio | Deleted routes | checkweb green after each batch | 2.0–4.0 | Low |
| 6.2 | Delete commerce web services, components, hooks, API route handlers | 6.1 | Clean src | checkweb green | 1.5–3.0 | Low |
| 6.3 | Remaining NIL bases + web services on the canonical chain (D3): ComplianceApiSingleton, InstitutionApiSingleton, SponsorApiSingleton, FanApiSingleton + their services | D3 | Base classes + services | Each extends the correct NIL base; CI base-check passes | 0.8–1.5 | Medium |
| 6.4 | proxy.ts + PLATFORM_DOMAINS; AuthContext / ServerResolvedContextProvider; UnifiedCapabilityService; rbac.ts | 6.3 | Updated infra | Auth flow works against the new Auth0 tenant; capability requests use NIL keys | 0.5–1.0 | Medium |
| 6.5 | Navigation links reseeded for NIL sidebars | 6.4 | Reseeded nav | Every sidebar item correct per FRONTEND_SPEC.md §8.3 | 0.3–0.6 | Medium |
| 6.6 | Rebrand: colors, logo, fonts, email templates, Sentry project | 6.4 | Rebranded UI | Zero VisibleShelf branding remains | 0.5–1.0 | Medium |

### Stage 7 — Credibility Shell

Entry: G6. Exit: G7. Estimate: 2–3 ew. (= spec Stage E / Phase 1)

| ID | Task | Depends | Deliverable | Acceptance | ew | Conf |
| --- | --- | --- | --- | --- | --- | --- |
| 7.1 | Marketing landing route + NIL brand domain in proxy.ts env config | 6.4 | Landing segment | TLS handshake + 200 on landing | 0.5–0.8 | Medium |
| 7.2 | Lead intake form (athlete/parent vs sponsor vs investor) → NilLeadService → nil_leads_list | 3.7, 7.1 | Form + route + Zod schema | Lead writes succeed; no PII publicly readable | 0.5–0.8 | Medium |
| 7.3 | nil_landing capability, full 8 phases (second capability — now templated from S5.5) | 5.5, 7.2 | Capability | verify-capability-deployment checklist passes | 0.5–0.8 | Medium |
| 7.4 | Investor-facing shell review: state coverage, responsive breakpoints, a11y | 7.3 | Reviewed shell | skill-frontend-ux-guardrails checklist passes | 0.3–0.6 | Medium |

Optimization visible here. nil_landing is the second capability built. With S5.5 as the reference implementation, its cost drops from a template-establishing exercise to an analogy. Tasks 7.3 and the five S9.2 capabilities all benefit from the same template.

### Stage 8 — Native Pipeline Breadth

Entry: G7. Exit: G8. Estimate: 2.5–5 ew. (= remainder of spec Stage F / Phase 2 beyond the slice)

| ID | Task | Depends | Deliverable | Acceptance | ew | Conf |
| --- | --- | --- | --- | --- | --- | --- |
| 8.1 | Media + metrics + achievements: models, services, submission paths | 2.2 | Services + routes | Media defaults pending; achievements feed the profile only when approved | 0.6–1.2 | Medium |
| 8.2 | athlete_tenant_memberships_list + AthleteMembershipService (transfers) | 2.2 | Service + routes | Transfer preserves history; cross-tenant row visible to both tenants | 0.4–0.8 | Medium |
| 8.3 | Institution roster management + admin/compliance roster controller | 8.2, 5.5 | Controller UI + routes | Status toggle triggers per-athlete cache eviction | 0.5–1.0 | Medium |
| 8.4 | Manual compliance verdict workflow (ComplianceVettingService full) | 3.7 | Workflow | No profile reaches approved without a verdict | 0.3–0.6 | Medium |
| 8.5 | Remaining P0 gates: non-allowlisted video host rejected; unmoderated media never public | 4.5, 8.1 | P0 tests | Both negative paths pass | 0.3–0.6 | Medium |
| 8.6 | RLS follow-through per D1 (if option 2: implement the deferred policies; if option 1: write the Phase-4 handoff note) | 2.8 | Policies or handoff note | Non-vacuous isolation test (option 2) or documented deferral (option 1) | 0.4–0.8 / +1–2 | Medium |

M2 milestone: a guardian can create an athlete-tenant, grant scoped consent, pass moderation + compliance, and see the athlete on the public roster — with every P0 negative-path test green.

### Stage 9 — Unified Service

Entry: G8. Exit: G9. Estimate: 12–20 ew. (= spec Stage G / Phase 3)

| ID | Task | Depends | Deliverable | Acceptance | ew | Conf |
| --- | --- | --- | --- | --- | --- | --- |
| 9.1 | athlete_tenant_memberships_list transfers + multi-guardian edge cases | 8.2 | Service hardening | Most-restrictive-wins verified with conflicting guardians | 0.4–0.8 | Medium |
| 9.2 | Five persona capabilities, 8 phases each (D6): nil_recruiting, nil_sponsorship, nil_achievements, nil_compliance (auto-ready), nil_finance (per D9). nil_guardian / nil_fan_network are platform-default, not gated | 5.5 (template), D6 | Capabilities | verify-capability-deployment passes per capability; template-then-analogy, not independent design | 3.0–5.0 | Low |
| 9.3 | Six per-actor dashboards (guardian, athlete, institution, sponsor, fan, compliance) reusing CrmPageShell/CrmNavPanel + the 5 standard panels (FRONTEND_SPEC.md §3a) | 6.4, 9.2 | Dashboards | No polling loop; unread via getReadState; scoped per base; server-resolved context | 3.0–6.0 | Low |
| 9.4 | CRM deltas: athlete_tenant_id/guardian_id columns + guardian-required trigger + tenant_nil_crm_options_settings; NIL CRM surfaces (Compliance / Institution+Sponsor / Guardian); nil_crm capability | 2.6 | Services + routes + capability | Minor-subject ticket without guardian → DB error; PII never projected without a consented relationship | 1.0–2.0 | Medium |
| 9.5 | Bot deltas: conversation athlete/guardian scoping + is_minor_safe + tenant_nil_bot_options_settings; 4 personas (Compliance/Eligibility, Guardian Onboarding, Recruiting/Sponsor FAQ, Fan); bot_guardrail_rules seed; nil_bot capability | 2.2 | Bot configs + RAG + capability | No minor PII in responses; unanswered → CRM escalation; guardrails at the RAG retrieval filter, not just the prompt | 1.0–2.0 | Medium |
| 9.6 | Invitations: InvitationService (lifecycle, guardian consent gate, anti-spam) + 9 routes + 5 FE components + 6 email templates + 6 connection-establishment side effects (each with its cache-invalidation obligation) | 9.2 | Invitation subsystem | Create/accept/reject/withdraw/guardian-approve work; minor cannot self-accept; 30-day re-invitation block enforced; each connection type creates the correct row + fires invalidation | 2.0–3.5 | Low |
| 9.7 | Onboarding: OnboardingService (actor-aware state machine) + 3 routes + OnboardingWizard + OnboardingProgressBanner | 9.6 | Onboarding subsystem | Per-actor step sequences return correct completion %; skip works for non-blocking steps | 1.0–2.0 | Low |
| 9.8 | Cross-cutting sweep: observability, cache correctness, i18n for compliance/bylaw copy | 9.2 | Sweep report | Every standing rule in §2.4 verified | 0.5–1.0 | Medium |

9.6 is the sleeper. Invitations and onboarding are described in the spec as one Phase-3 sub-feature. They are a bidirectional subsystem with nine routes, six side effects, six email templates, and a consent gate. Budget them as their own workstream.

### Stage 10 — Post-MVP (outline only)

No estimates. Listed so nothing is silently dropped. Full scoping is a separate exercise after G9.

- Automated compliance vetting (ComplianceVettingService auto + nil_eligibility_rules_list expansion per state/association)

- Financial infrastructure: deal-as-purchase transaction fee, EscrowLedgerService double-entry, guardian KYC/W-9, payout routing, non-profit pool slice

- RLS implementation (if D1 = option 1) across all athlete-owned + cross-tenant tables

- DataErasureService cascade + certificate

- Age-out job (18 → athlete gains financial scope, consent ledger preserved)

- Advanced abuse detection / scraping defense / rate-limit tuning

## 5. Optimizations Applied

Each is a concrete change from the spec's approach, with the saving it produces.

| # | Optimization | Replaces | Why it saves |
| --- | --- | --- | --- |
| O1 | API-first hybrid sequencing (S1–S3 → S4–S5 → S6) | Full extraction before any feature work | Surfaces architectural error at ew ~10 instead of ew ~26. Keeps a compiling web app throughout, so the destructive web pass is isolated |
| O2 | Template-first capability: build nil_roster end-to-end as the reference, then produce the other 10 by analogy | 11 independently-designed capabilities | One design decision plus ten analogies instead of eleven designs. Largest single saving in S9 |
| O3 | Automated PII/public-surface enumeration (S4.6) as a repeatable CI gate | One-time manual audit + DTO snapshot test | Repeatable, covers non-route surfaces, and catches regressions after G5 |
| O4 | Additive-then-subtractive schema sequencing (§2.2) | Spec's M1/M2 split (delete models and code together) | Two ordered, independently-verifiable repairs instead of one entangled cascade |
| O5 | Tenant guard instead of Phase-2 RLS (S4.1, default D1) | 24 RLS policies + GUC plumbing + Supabase transaction-mode workaround in Phase 2 | Equivalent bug-catch power at ~1 ew instead of ~3–6 ew plus an unsolved pooling problem |
| O6 | Single canonical base chain; delete V2/Stable (S0.4, D3) | Three coexisting chains carried into the fork | Removes drift and prevents new NIL bases from targeting an abandoned chain |
| O7 | Table-driven ID generator tests (S3.3) | Per-generator ad-hoc verification | 19 generators verified by one parameterized test |
| O8 | CI gates from commit 1 (S0.3), each gate-tested against a deliberate violation | Adding gates later | The source repo's type-level health eroded precisely because the deploy build masks errors (F3). Gates added late never get adopted |
| O9 | Hygiene purge before extraction (S0.4) | Cleaning up at the end | 509 backup files make every grep gate and every "did we get them all?" verification noisy |
| O10 | Spike-measured repair ratio (S0.1) | Guessing the deletion tax | Converts the two lowest-confidence estimates into measured ones |
| O11 | Re-baseline S6–S9 after G5 (§6.5) | Committing to the full estimate up front | ~44 ew of the estimate sits in Low-confidence stages; velocity after the slice is real data |
| O12 | Deferred nil_finance/auto-compliance to S10 | Pulling Phase-4 finance into the MVP | Keeps the MVP about the safety core, not money movement. D9 (fee params) is explicitly non-blocking |
| O13 | Evidence artifact per gate (§3) | "Stage complete" by assertion | Makes gate passage auditable and prevents silent scope erosion |
| O14 | Decisions ledger with defaults (§1) | Open questions blocking stages | No stage blocks on silence; the default is adopted in writing and the plan proceeds |
| O15 | Server-resolved context for all dashboards (S9.3) | Client polling | Prevents the ~1/sec request storm the spec itself flags (§12.11) |
| O16 | Pull the Credibility Shell forward (§2.1): run S7 immediately after S3, in parallel with S4–S5 | Shell at the end of the plan (~36.5 ew cumulative) | Implementation Phase 1 is explicitly investor-facing, and S7 has no dependency on the slice. Investor-ready public site at ~3 months instead of ~8. Zero cost in total effort — sequencing only |

## 6. Effort

### 6.1 Estimate by stage

| Stage | Low | Mid | High | Confidence | Dominant cost |
| --- | --- | --- | --- | --- | --- |
| S0 Baseline, hygiene, decisions, spike | 1.5 | 2.0 | 2.5 | High | Spike + hygiene + CI gates |
| S1 Infrastructure | 1.0 | 1.5 | 2.0 | High | Auth0 8-role wiring; Doppler parity; proving the fork deploys |
| S2 Schema Foundation | 4.0 | 6.0 | 8.0 | Low | Schema surgery + seeds + the RLS decision |
| S3 API Extraction & Core | 6.0 | 9.0 | 12.0 | Low | The deletion-and-repair loop across 542 route files / 361 services |
| S4 Safety Substrate | 2.0 | 3.0 | 4.0 | Medium | Tenant guard, consent engine, harness, PII enumeration |
| S5 Vertical Slice Validation ★ | 2.5 | 3.5 | 4.5 | Medium | The thin end-to-end path + 3 P0 gates + web slice |
| S6 Web Extraction & Core | 6.0 | 9.0 | 12.0 | Low | Same repair loop at 168,776 LOC / 436 pages / 303 services |
| S7 Credibility Shell | 2.0 | 2.5 | 3.0 | Medium | Landing + leads + second capability |
| S8 Native Pipeline Breadth | 2.5 | 3.5 | 5.0 | Medium | Media/metrics/achievements + roster mgmt + manual compliance |
| S9 Unified Service | 12.0 | 16.0 | 20.0 | Low | Breadth: 5 capabilities, 6 dashboards, CRM, bot, invitations, onboarding |
| Total (S0–S9) | 39.5 | ≈56 | 73.0 |  |  |

### 6.2 Correction to the v1 analysis

SPINOFF_MVP_ANALYSIS.md §5.3 reported a midpoint of ~48 ew; the correct midpoint of its own ranges was ~52 ew (extraction 26.25 + feature 25.5) — an arithmetic slip in that document's summary line.

This plan's midpoint is ~56 ew, i.e. +4 ew over the corrected v1 figure. The increase is deliberate and traceable:

| Change | Δ ew (mid) | Why |
| --- | --- | --- |
| S0 (baseline, hygiene, decisions, spike) added as a stage | +2.0 | Previously implicit in "extraction"; the spike and hygiene pass are real work |
| Safety substrate (S4) + slice (S5) + breadth (S8) replace the single "Stage F" line | +3.0 | The v1 figure of 5–9 ew for the entire native pipeline was optimistic by omission — it did not carry the tenant guard, the negative-path harness, or the PII enumeration as explicit line items |
| Total | +5.0 | Offset by O2/O4/O5 savings already reflected in the per-stage numbers |

Reporting the increase explicitly is the point: the v1 number was low for reasons, and hiding that would repeat the spec's own error (F11).

### 6.3 Backend / web split

The backend is not half the work — it is roughly two thirds, because schema, API extraction, and the safety core dominate and are shared.

| Slice | Stages included | Low | Mid | High |
| --- | --- | --- | --- | --- |
| Backend / API — infra, schema, API extraction, safety substrate, slice (API), shell (API), native pipeline, unified service (API) | S0, S1, S2, S3, S4, S5 (API), S7 (API), S8, S9 (API) | 26.0 | 37.5 | 49.0 |
| Web / frontend — slice (web), web extraction, web bases/services, landing + roster UI, 6 dashboards, ~44 components, nav, rebrand | S5 (web), S6, S7 (web), S9 (UI) | 13.5 | 19.0 | 24.0 |
| Total |  | 39.5 | ≈56 | 73.0 |

### 6.4 Calendar scenarios

Assumes decisions are made on time. S2→S3→S4→S5 is a hard chain; S6 and S9 parallelize.

| Team | Calendar (mid, ~56 ew) | Notes |
| --- | --- | --- |
| 1 engineer | 12–17 months | Fully serialized on the S2→S5 chain |
| 2 engineers (backend, web) | 7–10 months | Web is idle during S2–S5 — consider starting S6 prep in parallel |
| 3 engineers (backend, web, safety/QA) | 5–8 months | Best fit. Safety/QA owns S4.6/S4.7 and the P0 suite from S2 onward |
| 4 engineers (+ data/platform) | 4.5–7 months | Diminishing returns; the chain does not widen |

### 6.5 Re-baselining rule (O11)

After G5, re-estimate S6–S9 from measured velocity. S2, S3, S6 and S9 are Low-confidence and carry ~44 ew of the ~56 ew midpoint. By G5 you have measured:

- the actual repair ratio (S0.1 predicted it; S3 confirmed it)

- the real schema surgery cost (S2)

- capability cost for one full 8-phase implementation (S5.5)

- slice velocity per task

Feed those into S6–S9 and reissue §6.1. Do not treat the numbers above as a commitment beyond G5. Treating them as one is exactly the failure mode documented in F11.

### 6.6 Cost

Effort converts to money in the companion document BUDGET.md. Headline figures for the recommended delivery shape (2 human engineers + 3 agent seats), using the illustrative loaded rate of $3,000/ew:

|  | Mid | Range |
| --- | --- | --- |
| MVP build (labor + agents + infra + legal) | ~$168,000 | $128,000–224,000 |
| — of which human engineering labor | ~$130,000 |  |
| — of which legal review (parameter — hold open until quoted) | $30,000 | $15,000–60,000 |
| Post-launch infrastructure run-rate | ~$150–600/month |  |

Three things in that document change how this plan should be executed:

- Budget agent capacity by usage, not seats. Anthropic's published enterprise data puts observed Claude Code cost at $150–250/developer/month with the seat fee only ~8–12% of the total. A $20 seat can produce a $250 bill. Use $200–400/seat-month all-in.

- ~34 of the 56 ew midpoint is agent-suitable; ~22 ew is human-owned. BUDGET.md §4.1 maps this per stage. The human-owned portion is S4 (Safety Substrate) and S5 (Vertical Slice) plus the review tax — and it is the part that is not compressible.

- Optimization O2 (template-first capability) is the single largest source of agent leverage — one reference implementation, then ten near-copies. It is worth doing well for that reason alone, not just for the direct time saving.

The S0.1 spike should also measure agent effectiveness. Have the agent perform the deletion-and-repair, and record agent-hours, human review-hours, and defects found. That replaces BUDGET.md parameters 6 (E, the effectiveness multiplier) and 7 (T, the review tax) with measured values — the same 3–5 days the plan already recommends, now paying off twice.

## 7. Verification & Evidence Standard

### 7.1 Test layers

| Layer | Tool | Covers | Where |
| --- | --- | --- | --- |
| Typecheck | tsc --noEmit via pnpm checkapi / pnpm checkweb | Both apps, zero errors | CI, every PR |
| Unit | vitest | ID generators, pure helpers, mappers, resolvers | apps/api, apps/web |
| Integration (API) | vitest + test DB | Services, consent engine, firewall transitions, capability routes | apps/api |
| DB-level | vitest + test DB | Tenant guard rejection, guardian-required trigger, MV scoping | apps/api |
| P0 negative paths | vitest + harness (S4.7) | The five §12.12 P0 tests | Release-blocking |
| Component render | vitest + renderToStaticMarkup | Web components (no jsdom — see D8 / AGENTS.md) | apps/web |
| Static gates | grep / AST script | Raw fetch, UUID ids, PII on /api/public/*, NIL-base compliance | CI, every PR |

### 7.2 P0 release-blocking suite (from TECHNICAL_SPEC.md §12.12)

- ☐ Under-13 athlete cannot be registered without prior verifiable guardian consent → 403

- ☐ No messaging thread between an adult role and a minor can exist without a guardian participant (structural invariant)

- ☐ Consent revocation removes the profile and all media from public surfaces within one request and evicts every cache namespace

- ☐ Deal creation is blocked where nil_eligibility_rules_list.deals_allowed = false

- ☐ Media cannot publish without moderation clearance; non-allowlisted hosts rejected

A stage cannot ship with any of these red — even if it is functionally working.

### 7.3 Frontend verification constraint

apps/web has no jsdom and no testing-library (per AGENTS.md). Component tests server-render via renderToStaticMarkup; useEffect never runs; Radix/Accordion/Tabs panels unmount when inactive. Consequences the plan must live with:

- Assert on serialized markup (value="…" attributes, copy presence), not on interaction

- Use initialTab / initialOutcome-style props to reach state-gated panels without interaction

- Extract pure helpers and data-contract mappers into named exports and unit-test those instead of the component

- The FRONTEND_SPEC.md §14 checklist items that are interactional or layout-based ("no page-level horizontal overflow", "mobile 320px / desktop 1440px intentionally designed") are not expressible in this harness. They require manual review at S7.4, recorded as a signed checklist — not a passing test

If the project wants automated interaction/layout testing, that is a deliberate dependency decision (D8), made once, not discovered per-component.

## 8. Gap Closure Matrix

Every finding from SPINOFF_MVP_ANALYSIS.md maps to the task or gate that closes it. No finding is left to chance.

| Finding | Severity | Closed by | How |
| --- | --- | --- | --- |
| F1 RLS premise is false; spec points at commented-out dead code | Critical | D1, S2.8, S4.1, S8.6, SPEC_AMENDMENTS.md TS-1/TS-8/MD-4 | Decision ledger resolves it; tenant guard substitutes in Phase 2; RLS deferred to S10 or budgeted honestly; source docs corrected |
| F2 No tenant_type; tenants is commerce-shaped; directory_visible defaults true | Critical | D2, D5, S2.1, S2.5, TS-9 | Side table + platform_default tier + forced directory_visible=false + MV scoping test |
| F3 Build masks TS errors; checkapi is the only real gate | High | S0.2, S0.3, O8 | Green baseline captured; typecheck gate installed and gate-tested from commit 1 |
| F4 Spec file references stale or non-existent | High | S2.3 (corrected paths), §2.3, SPEC_AMENDMENTS.md TS-4/TS-7/MD-6 | Every path replaced with a verified one before it is used in a DoD |
| F5 Three coexisting base-singleton chains | High | D3, S0.4, S6.3, §2.4, TS-10/MD-2 | Canonical chain chosen; abandoned variants deleted; NIL-base rule enforced in CI |
| F6 Five internal spec contradictions | High | §1 (D1, D3, D6), §2.3 (bot UUID exception), SPEC_AMENDMENTS.md | Each contradiction resolved to one authoritative answer; losing text amended |
| F7 orders/payments rename drags entanglement | Medium | D4, S2.2, S3.6, MD-3 | Create nil_deals/nil_deal_milestones/nil_payments fresh; delete commerce models; reuse services |
| F8 509 backup files + backup Prisma models carried into the fork | Medium | S0.4, O9 | Hygiene purge before extraction |
| F9 Non-route PII surfaces unswept (MV, directory, nav, email, Sentry, audit/erasure conflict) | Critical | D5, D7, S2.5, S2.7, S4.6, S4.8, O3 | Automated enumeration script as a CI gate; MV scoping test; audit rows pseudonymous; erasure reconciliation designed at schema time |
| F10 P0 tests have no harness; frontend harness constrained | Medium | D8, S4.7, §7.3 | Harness built before the features it guards; web constraints documented and the interactional checklist routed to manual review |
| F11 Estimates exist only for extraction, and are ~an order of magnitude low | Low | §6 (this plan), O10, O11 | Effort published for every stage; spike measures the tax; S6–S9 re-baselined after G5 |
| F12 NIL model count undercounted | Low | S2.2 | Tables counted directly from TECHNICAL_SPEC.md §14 before the migration is written |

## 9. Traceability

Stage → source documents, so nothing is silently dropped from the original plan.

| This plan | Spec stage | Source |
| --- | --- | --- |
| S0 Baseline & hygiene | (new) | SPINOFF_MVP_ANALYSIS.md §5.6, §6 items 1/4/11; F1–F12 |
| S1 Infrastructure | Stage A | MIGRATION_DESIGN.md §1 (M0); PROJECT_SEQUENCE.md A |
| S2 Schema Foundation | Stage B | MIGRATION_DESIGN.md §3 (M1); PROJECT_SEQUENCE.md B; TECHNICAL_SPEC.md §14, §18 |
| S3 API Extraction & Core | Stage C | MIGRATION_DESIGN.md §4 (M2); PROJECT_SEQUENCE.md C; TECHNICAL_SPEC.md §6, §7, §9 |
| S4 Safety Substrate | (new — distributed in spec) | TECHNICAL_SPEC.md §3, §8, §12.6–12.8, §12.12; IMPLEMENTATION_PLAN.md 2.13–2.15 |
| S5 Vertical Slice | (spec's "First Executable Slice") | PROJECT_SEQUENCE.md "First Executable Slice"; TECHNICAL_SPEC.md §8, §10 |
| S6 Web Extraction & Core | Stage D | MIGRATION_DESIGN.md §4.7–4.9 (M3); PROJECT_SEQUENCE.md D |
| S7 Credibility Shell | Stage E / Phase 1 | PROJECT_SEQUENCE.md E; TECHNICAL_SPEC.md §4 Phase 1 |
| S8 Native Pipeline | Stage F / Phase 2 | PROJECT_SEQUENCE.md F; TECHNICAL_SPEC.md §4 Phase 2, §12.12 |
| S9 Unified Service | Stage G / Phase 3 | PROJECT_SEQUENCE.md G; TECHNICAL_SPEC.md §4 Phase 3, §15–§18 |
| S10 Post-MVP | Stage H / Phase 4 | PROJECT_SEQUENCE.md H; TECHNICAL_SPEC.md §4 Phase 4 |

## 10. Risk Register (v2)

Ordered by expected impact. Each has a trigger — the observable signal that the risk is materializing — so mitigation starts before the damage.

| # | Risk | Sev | Likelihood | Trigger | Mitigation | Contingency |
| --- | --- | --- | --- | --- | --- | --- |
| R1 | RLS assumed present, is absent → Phase-2 privacy guarantee weaker than documented; isolation tests pass vacuously | Critical | Certain (verified) | Any test asserting isolation that passes with zero rows visible | D1 + S4.1 tenant guard + non-vacuous test requirement (S2.8) | Build RLS in S2 (+3–6 ew) and slip S7 |
| R2 | Deletion-and-repair tax exceeds estimate | High | High | S0.1 spike ratio > 3× spec assumption; a batch takes > 1.5× its estimate | O10 spike; §2.2 additive-then-subtractive; batch with checkapi per batch | Cut breadth: ship S1–S8, defer S9 capabilities to a second release |
| R3 | Minor data reaches a public surface via a non-route path | Critical | Medium | S4.6 enumeration reports an unclassified surface | S4.6 automated gate + S2.5 MV scoping test + D5 exclusion + D7 pseudonymous audit | Halt S6; treat as a release blocker |
| R4 | tenant_type / athlete-tenant tier semantics left ambiguous | High | High | Capability resolver called with an athlete-tenant and returning a tier-shaped answer | D2 + S2.1 + S2.3 platform_default tier | Add an explicit actor-type guard to the resolver |
| R5 | Spec instructions remain internally contradictory → wrong variant of a safety control implemented | High | High | Implementer asks "which document wins?" | §0.2 conflict rule + SPEC_AMENDMENTS.md + §1 decisions ledger | Freeze the spec set; re-issue amendments before continuing |
| R6 | Consent revocation cascade is partial → stale minor data publicly cached | Critical | Medium | A revoke test passes but a different namespace still serves the profile | S4.4 enumerated contract + P0 cascade test (release-blocking) | Halt feature work; fix eviction completeness before proceeding |
| R7 | Erasure vs. immutable audit trail unreconciled | High | Medium-High | Legal review flags it, or an erasure request cannot complete | D7 + S2.7 pseudonymous references designed at schema time | Retrofit = data migration; avoid by deciding in S0 |
| R8 | State NIL law changes mid-build | High | High (inherent) | A state passes/amends HS NIL legislation | Data-driven nil_eligibility_rules_list — no bylaw logic in code | Seed update only; no code change |
| R9 | Frontend verification gap → UX guardrails silently skipped | Medium | High | Components merged with no state/layout evidence | D8 + §7.3 + S7.4 signed manual checklist | Add jsdom deliberately (a D8 revision) |
| R10 | Bot/RAG leaks non-consented athlete data | Critical | Medium | A bot response contains a non-consented field | Guardrails at the RAG retrieval filter, not the prompt; is_minor_safe default true | Disable nil_bot capability until fixed |
| R11 | Supabase pooler transaction mode breaks the tenant-context mechanism | Medium | Medium | GUC does not persist across a pooled query | Resolve in S2.8 before scheduling RLS | Use a direct connection for RLS-scoped work |
| R12 | Fork inherits dead weight → noisy gates, duplicate models, incomplete sweep | Medium | Certain (verified) | Any grep gate returning .bak noise | S0.4 hygiene purge | — |
| R13 | A pilot dataset exists after all | Medium | Low | Supabase project is not empty | D11 confirmed at S0 | Void the estimate; re-plan with a data-migration stage |
| R14 | Auth0 8-role mapping breaks after the fork | Medium | Medium | A role fails to resolve on the new tenant | S1.3 + S3.8 + G1 round-trip | Fix at S1 — do not carry a broken auth into S3 |

## 11. Change Control

| Change type | Process |
| --- | --- |
| Task-level (reorder, split, re-estimate a task) | Update this document; note the reason in the stage PR |
| Gate change (exit criteria relaxed) | Requires the plan owner's explicit sign-off, recorded in this document. Relaxing a P0 criterion is not permitted without a written risk acceptance |
| Stage insertion/removal | Requires the plan owner's sign-off + a re-issued §6 estimate |
| Decision override (a D-number) | Update §1 with the override, the rationale, and the date. Overrides that contradict a SPEC_AMENDMENTS.md entry require that entry to be revised too |
| Finding closure disputed | Re-open the finding in SPINOFF_MVP_ANALYSIS.md, mark §8 here as contested, and re-verify against the repo before proceeding |

Re-baseline checkpoint. §6.1 must be re-issued after G5 (§6.5). A stage that begins after G5 using the pre-G5 estimate without a re-baseline is a plan violation.

## 12. Summary

| Question | Answer |
| --- | --- |
| Is the approach sound? | Yes. Pattern replication of a verified-capable platform, with athlete-as-tenant as the isolation root |
| Is the plan executable now? | Yes. Every blocking decision has a recommended default (§1); every finding has a closing task or gate (§8); every stage has an entry gate, exit gate, and evidence artifact (§3) |
| Build order | Hybrid (API-first): S1–S3 extract API + schema, S4–S5 validate a vertical slice, S6 extracts web, S7–S9 add breadth |
| Estimated effort | 39.5–73 ew, likely ~56. Backend ~37.5 ew (⅔), web ~19 ew |
| Calendar | 3 engineers: 5–8 months. Solo: 12–17 months |
| When is the estimate trustworthy? | After G5. ~44 of ~56 ew sits in Low-confidence stages; re-baseline S6–S9 from measured velocity (§6.5) |
| The single highest-value action | S0.1 — the 3–5 day extraction spike. It converts the two lowest-confidence estimates into measured numbers and produces the coupling map S2 needs |
| The single highest-risk item | R1 / F1 — resolve the RLS premise (D1) before S2 begins. Do not carry the false premise into the fork |
| What must not slip | D10 legal review. External, longest lead time, hard-gates the S2 schema freeze |